## Concept
Goal of Risk Management is looking forward to anticipate future problems and structuring the project to avail or mitigate potential problems. Risk Matrix is a proactive team activity that helps everyone understand the project and potential pitfall better. Frequently this is when the scope of a project is finally firmed up after all potential risks are mitigated or avoided.
A Risk can be something that impacts a project negatively or positively (example: vendor runs late or sales take off before we have production capacity built.
There are four way to address a Risk:
Mitigate - put something in place so it won't happen or if it does happen you are ready to address it.
Avoid - scope the project such that it is no longer a risk or if an upside risk your team is ready to handle the growth.
Transfer - use insurance or hire a vendor who is really good at it
Accept - only if it is low severity and likelihood may a risk be accepted with no other strategy spelled out.
Once the strategy is determined, write it up so if / when the risk happens, it becomes an issue but you have a plan on what to do in advance. It allows your team to act immediately.

## Risk Matrix
This is an example, please add yours to the bottom and then once you are comfortable, you can erase the example lines. | [7 empty] | Risk Matrix
[8 empty] | Likelihood | Place the Risk Number on the Risk Matrix.
[8 empty] | High |  |  | 2
| Project Title - Example | [9 empty] | 1,3,4
5
Low
[9 empty] | Low | Severity |  | High
Risk Number | Risk Title | Description | Likelihood (1-5) | Severity (1-5) | Action to take | Details | Notes
1 | Unknown in our first upgrade on servers | Consultant helped last time and we have not done an upgrade to DegreeWorks since | 3 | 3 | Mitigate | 1) Seth will ask for tips and hints from support 2) Sally check with user community 3) Sally contact consultant - are you available if needed? Do you know of any issues? | 11/10/16 Started on these mitigations. |  | No project should go forward until risks in the Red zone are mitigated, avoided, or transferred in such a way that it lows the risk to yellow or green.
2 | Not being able to complete the Dev environment by 12/9 | Waiting on Ellucian plus waiting on Angie to complete (e.g. web server issues) | 5 | 3 | Mitigate | 1) Review settings (Judy and Corey help back fill) 2) Angie engage coworkers on specialty areas like Tomcat | 11/18/16 Started now. Completed |  | Tips:
3 | Localizations - unknown how well they will translate with new version | Unknown issues | 3 | 3 | Mitigate | Judy will research in advance of starting the project | 11/10/16 started / Completed |  | It is wise to ask for help the first few times you lead your team through Risk management activities. There are week long classes on how to address Risks but it is best learned by doing it with a mentor who will facilitate the first one for you, then assist you on the second one, etc..
4 | Ban80s - unknown how well they will translate with new version | Unknown issues | 3 | 3 | Mitigate | JJ will research in advance | 11/10/16 started / completed
5 | Unknown issues occur after 2/18 go live | If there are unknown issues after go live, we can roll back to 4.1.4 | 2 | 3 | Mitigate | Angie and technical team will be able to roll back to 4.1.4 so RO can meet their 3/1 due date of having Freshman four year plans ready. | 2/2/17 team meeting
Second point - prime the pump with a risk you know could occur on the project as an example.
Explain an Issue has happened, a Risk has not yet occurred.
Strategy may be Avoid, Mitigate, Transfer or lastly Accept only if in the Green zone.

## Stakeholders
Project Stakeholders
Select As Required
| Name | Title | Preferred frequency of updates | Preferred media | Governance | Influencer | User/Beneficiary | Development | Provider
Example | Toney Flack | CIO | Bi weekly | Portfolio review meeting | X | x
X
X
[6 empty] | X | X
[6 empty] | X | X
[6 empty] | X | X
X
X
X
X
X
X
X
X
X
X
Looking at Stakeholders frequently drives out Risks and additional work that should be added to the Plan, included needed communication.
Tip: Ask what could go wrong in this Stakeholder's area? What might this stakeholder be worried about?

## How To In TDX
Who | How | When | Tip: If you are not using Teamdynamix you may just use this Risk Matrix tab.
Person filling out the Project Request | After the initial form is completed, a section called Risk is optional to fill out on the Project Request | When project request is first submitted, frequently market timing is a risk known by the requestor
ITS Resource managers or directors | Completing information to determine what's needed, part of the Project Charter sections call Organizational Risks which affect the scorecard of the project. Also any approver may click on Risk Register and add one. | When project is being reviewed for selection
Project Manager | When forming the team and project, work with the team to gather and address all known risks: Select Project, Manage, Risks, +New which will populate the Risk Register. | Generally the second meeting of the team
Sponsor | Client portal, Select Projects, Open project, click on Risk, +New | Any time one is thought of; it is then the PM's responsiblity to work with the team to address and assign it.
Stakeholder | Client portal, Select Projects, Open project, click on Risk, +New | Any time one is thought of; it is then the PM's responsiblity to work with the team to address and assign it.
Team member | Client portal, Select Projects, Open project, click on Risk, +New | Any time one is thought of; it is then the PM's responsiblity to work with the team to address and assign it.

## DropDown Lists
Severity and Likelihood
High
Medium High
Medium
Medium Low
Low