## Slide 1: INTRODUCTION
Kevin Saal
Director of Athletics
Cell-859.338.4949
Email – ksaal@goshockers.com
Clay Stoldt
Faculty Athletics Representative
316.978.5441
Email-clay.Stoldt@Wichita.Edu
Notes: Clay

## Slide 2: TIMELINE & PROGRESS
PAST
  2020 Interim President Muma Constituted the Athletics Policy & Task Force
    Composed of athletics department, university staff and students
    Examine Athletics Department policies, practices & organizational climate
    Conduct self-report climate study
  Athletics Policy & Task Force Recommendations
    41 recommendation in the following areas
      Reporting & Procedures
      Policies & Statements
      Additional Resources, Trainings and/or Organizational Best Practices
      Recommendations for the American Athletic Conference
    Recommendations Summarized in a Matrix
Notes: Clay

## Slide 3: TIMELINE & PROGRESS
PRESENT
  August of 2022
    New Director of Athletics Kevin Saal Established an Implementation Committee
    Converted the APC Task Force’s Matrix into an Implementation Matrix
    Began work to implement 41 APC Task Force Recommendations
  CURRENT STATUS
    39 of 41 recommendations have been substantially completed
    Remaining work on the 2 outstanding items continues and will be completed by June 2023:
      Holistic Student-Athlete Development Trainings
        Post-Shocker Life Assessment
        16th Team – DEI Team
        1st Year Experience Course
      Athletics Coaches & Staff Training Program
Notes: Clay to note top point about Kevin establishing the Implementation Committee
Kevin to cover rest of August of 2022 section and Current Status

## Slide 4: TIMELINE & PROGRESS
FUTURE
  Comprehensive Review/Update of Timeline & Progress
    APC Task Force (DONE)
    Athletics Department Student-Athlete Advisory Committee (DONE)
    President’s Executive Team (June 2023)
    Student Government (DONE)
    Faculty Senate (DONE)
    Staff Senate (May 2023)
    ICAA Board (May/June 2023)
  Upload Implementation Committee Report to APC Task Force Website (May 2023)
  Annual Rhythm
    Reconvene Implementation Committee (February & September)
    Reconvene & Update APC Task Force (TBD)
    Update SAAC (TBD)
    Include Updates in Reports to Faculty & Staff Senates (TBD)
    Include Updates in Director of Athletics Report to ICAA Board (May)
Notes: Kevin

## Slide 5: Wichita State Athletics QUESTION & ANSWER
Kevin Saal
Cell-859.338.4949
Email – ksaal@goshockers.com
Clay Stoldt
316.978.5441
Email-clay.Stoldt@Wichita.Edu